## Sheet1
Project Name: | NutriPal
Project Start: | 2024-08-01
Student Number (NSBM): | 25993
Student Number (Plymouth): | 10898719
Task | Start Date | End Date | Days | Progress | time axis 2024-07-22 to 2024-12-24
Planning and Design
Define core features and functionalities | 2024-08-01 | 2024-08-02 | 1 | 100%
Idendify target audience and user persons | 2024-08-01 | 2024-08-02 | 1 | 100%
Establish technical requirements and platform | 2024-08-01 | 2024-08-02 | 1 | 100%
Create wireframes and mockups for key app screens | 2024-08-02 | 2024-08-03 | 1 | 100%
Design the user interface with a focus on usability | 2024-08-02 | 2024-08-04 | 2 | 50%
Define user flow and navigation | 2024-08-02 | 2024-08-05 | 3 | 100%
Finalize UI/UX designs | 2024-08-05 | 2024-08-06 | 1 | 100%
Set up the development environment and project repository | 2024-08-05 | 2024-08-06 | 1 | 100%
Choose tech stack and necessary tools | 2024-08-05 | 2024-08-06 | 1 | 100%
Core Development - User Authentication and Meal Planning
Implement user registration and login | 2024-08-06 | 2024-08-07 | 1 | 100%
Develop user profile setup | 2024-08-07 | 2024-08-08 | 1 | 60%
Integrate a secure authentication system | 2024-08-08 | 2024-08-09 | 1 | 100%
Develop the algorithm for generating personalized meal plans | 2024-08-09 | 2024-08-10 | 1 | 20%
Implement UI for displaying daily and weekly meal plans | 2024-08-10 | 2024-08-11 | 1 | 0%
Ensure that meal plans consider dietary restrictions and preferences | 2024-08-11 | 2024-08-12 | 1 | 0%
Core Development - Recipe Suggestions and Nutrition Traking
Build the recipe database | 2024-08-12 | 2024-08-13 | 1 | 0%
Develop AI-driven recipe suggestion feature based on user preferences and past choices. | 2024-08-13 | 2024-08-14 | 1 | 0%
Implement recipe detail view with ingredients, instructions, and nutritional information. | 2024-08-14 | 2024-08-15 | 1 | 0%
Implement functionality for logging meals and snacks | 2024-08-15 | 2024-08-20 | 5 | 0%
Develop the system for tracking macronutrients and micronutrients | 2024-08-15 | 2024-08-20 | 5 | 0%
Create the UI for displaying nutritional intake and progress towards goals | 2024-08-15 | 2024-08-20 | 5 | 0%
Additional features and backend development
Shopping List and Community Features | 2024-08-20 | 2024-08-21 | 1 | 0%
Backend integration and data storage | 2024-08-21 | 2024-08-22 | 1 | 0%
Notifications and Reminders | 2024-08-22 | 2024-08-23 | 1 | 0%
Testing, launch, preparation and launch
Testing and quality assuarance | 2024-08-23 | 2024-08-27 | 4 | 0%
final touches and optimization | 2024-08-23 | 2024-08-27 | 4 | 0%
Launch Preparation | 2024-08-27 | 2024-09-01 | 4 | 0%
App Launch | 2024-09-01 | 2024-09-01 | 0 | 0%